## Dashboard
AEC Strategy Implementation
2025/2026 Dashboard
1ST JAN 2026 TO 30TH SEPT 2026
Focus Area | Total Outcomes | Total Milestones | % Complete
Financial Stability | 4 | 6 | 65%
Youth Succession Planning | 6 | 34 | 53.33%
Wider Community Engagement | 7 | 24 | 55.71%
Building Teams & Leadership | 4 | 12 | 55%
Community Activities | 3 | 12 | 70%
Spiritual Focus | 6 | 13 | 64%
TOTAL | 30 | 101 | 60.51%

## Instructions
Tracker Instructions
Purpose
This workbook tracks delivery of AEC’s 2025–2026 strategy across six focus areas. All stakeholders can see the whole spreadsheet; please edit your own tab only
How to update
1) Click on your focus-area tab, adjust % bottom left to enable seeing all sections
2) Scroll down to see all streams. Add notes and modify sections as required; milestones, dates, owners etc.
Grey cells and risk levels are not to be changed, white cells can be amended by you. Some cells (status, % and risk cells) have drop down boxes for you to select options
3) Set Status and % Complete using drop down boxes
4) If actions are delayed, choose a Reason for Delay and add a brief note
5) When finished just close the spreadsheet, it is automatically saved. Cancel changes you made by using the Und button in the home tab of the spreadsheet. The Dashboard will update your completion % automatically
6) The Dashboard will update your completion % automatically
This video shows how to use the spreadsheet: | Watch Video
Please note: this document and the video are Confidential – Al‑Emaan Centre Internal Use Only. Not to be shared

## Financial Stability
ULTIMATE AIM : ESTABLISH DIVERSIFIED, SUSTAINABLE INCOME STREAMS SLT Lead Behzat | [9 empty] | Financial Stability
IS VALID | SMART Outcome | Benefit | Starting Point / Baseline | Department | Reported to OPEX | Responsible Person | Risk Level | Risk if Not Achieved | Target Date | Specific Desired Outcome | Milestone Count | Milestone/s | Milestone/s Date | Actions | Status | Reason for Delay | Complete % | Notes
YES | Establish diversified, sustainable income streams | Service provision, significant income stream to be invested in Waqf | Donation-dependent operations; limited reserves; no diversified income operational yet. Soft launch of TFS complete | Safa Holdings / Finance | End of March End of June End of Sept | Shaffiq | Medium | High | 2026-02-28 | Deliver a live Funeral Service: Tahreem Funeral Service (operational & marketed) | 3 | 1. Cement policies & procedures 2. Hard Launch 3. Full service provision + £ | 1. Jan - March 2. March 3. Mar - Sept | Continuous service improvement, additional fridge set up. Imam and Funeral Director to run roadshow prior to hard launch. Thorough marketing and relationship building- cemeteries, hospitals etc. Add our website link to other masajid and Eternal Gardens website | Complete |  | 100% | The launch included delivering 21 full funerals, tightening policies and procedures, adding fridges, creating leaflets, livening the website, sending emails and WhatsApp messages, building relationships with Shirley, Penge, Purley, MCWAS, Tunbridge Wells and Maidstone (including use of facilities at Maidstone and TW). Send messages to our community, making a popup for the AEC website, setting up Tahreem@group email, adding our details to the Eternal Gardens website, announcing at jumu'ah. Before hard laucnh we have made a net profit of £20k
YES | Establish diversified, sustainable income streams | Service provision, recurring advertising revenue + partnerships | Donation-dependent operations; limited reserves; no diversified income operational yet. Idea and website ready for Business Directory | Safa Holdings / Finance | End of March End of June End of Sept | Shaffiq | Medium | Medium | 2026-03-31 | Launch Green Pages Business Directory (100+ listings.) Launch through MosqueApp | 1 | Created website offering, Raja to launch and do intital pre registration checks | 2026-04-30 | Intro offer; outreach to local businesses; simple sign-up | In Progress |  | 90% | Raja is on this iA
NO | Grow current Waqf capital by £60,000 by Sept 2026 | Perpetual income for AEC | Donation-dependent operations; limited reserves; no diversified income operational yet. Curently contains £75k | Finance | End of March End of June End of Sept | Raja / Kamraan | Low | High | 2026-06-30 | Raise £60k additional funds for waqf investment | 0 | Ramadhan Waqf fundraising round 2 | Last 10 days of Ramadhan | Friday talks, create deck for last 10 days of Ramadhan | In Progress | The amount we wanted to raise in the last 10 days of Ramadhan was not realised |  | Will look to HNW network to achieve this
YES | Grow Waqf capital to £200,000 by Sept 2026 | Step-change in waqf investment amount | Donation-dependent operations; limited reserves; no diversified income operational yet. Curently contains £75k (+£60k Ramadhan iA) | Exec | End of March End of June End of Sept | Shaffiq | Medium | High | 2026-09-30 | Increase waqf investment by further £65k | 1 | HNW and individual investor approach pack + roadshows | 2026-09-01 | Curated deck; Brunei / Malaysian network, donor lunches; targeted HNW outreach | In Progress |  | 70%
YES | Achieve net-positive operating balance by Sept 2026 | Operational transparency + sustainability | Donation-dependent operations; limited reserves; no diversified income operational yet | Finance | End of March End of June End of Sept | Behzat / Raja / Kamraan | Low | Medium | 2026-09-30 | Monthly finance dashboard & cost controls | 1 | Ramadhan BAU fundraising Dashboard creation | 2026-09-01 | Budget discipline; procurement policy | In Progress |  | 0%

## Youth Succession Planning
ULTIMATE AIM : DEVELOP YOUTH LEADERSHIP + SUCCESSION PLANNING SLT Lead Avais | [9 empty] | Youth Succession Planning
IS VALID | SMART Outcome | Benefit | Starting Point / Baseline | Department | Reported to OPEX | Responsible Person | Risk Level | Risk if Not Achieved | Target Date | Specific Desired Outcome | Milestone Count | Milestone/s | Milestone/s Date | Actions | Status | Reason for Delay | Complete % | Notes
YES | Develop youth leadership | Pipeline of young leaders, succession planning | No formal youth leadership structure; involvement is ad‑hoc and reactive | Youth | End of March End of June End of Sept | Afsor | Medium | High | 2026-02-15 | Establish Youth Council (10 members) + Shadow Trustees + Key staff positions proteges allocated | 1 | Clear roles; mentor pairing; monthly meetings, Liaise with Madrassa, Scouts, Boxing and Taekwondo functions | Target end Ramadan for first results | Ramadan: Volunteer Request, Omar Youth talks > key to identify youth. Youth Experience event plan for post Ramadan. | In Progress |  | 80% | Results Ramadan> Youth activiites - building responsibility for the youth across the mosque. Demonstrated across youth events, running the coffee cart (i.e not just running, but also increasing product range to generate more "revenue" for the mosque), youth volunteers. How does this line with pipelne of young leaders: We have identified young leaders who we would recommend as part of a youth leadership strucutre that can support our growth. So based on we have identnfied caditates and now its about setting the strucutre, we have completed 40%, next 20% is setting structure, next 20% is executing it, and final 20% is ensuring its operating as part of the wider management teams. Q2: setting up youth board in progress.
YES | Increase youth volunteering team by 40% | Higher engagement & continuity | Current team number: X | Youth | End of March End of June End of Sept | Afsor | Low | Medium | 2026-06-30 | Quarterly youth volunteer drives | 1 | School/college outreach; buddy system | Target end Ramadan for first results | Ramadan - youth voltuneering kicked off. | In Progress |  | 60% | Q1:Results Ramadan: Youth volunteering from our advertising was not as successful but we had youth volunteering more by supporting the young adults i.e. Davids kids were helping coffee stand. We just need a bit more forward planning around youth volunteer requirements leading up to events, lead with young adults .. this will yield better results in future. Q2: We are building a core set of youth who are very engaged. Summer will be an important time to build events which bring our youth together.
YES | Targeted talks to attract youth | Higher engagement & building youth connection to masjid | Ad-hoc talks currently | Youth | End of March End of June End of Sept | Afsor | Medium | Medium | 2026-03-31 | Plan and deliver targeted talks for all youth demographics | 6 | 1 every 2 months | Target end Ramadan for first results | Working with Omar to create a better set of talks for youth. Focus is not purley on topic, but more on connecting them to mentors + people they can respect/look up too (people who are not to old). First test of this will be in Ramadan. | In Progress |  | 60% | Ramadan Resulst > Continue youth. Omar and Eni doing a great job. Think we need a sisters lead one switch at some point. 60% completion rate once we get consisten cy, have new people joining, 80% once we see engagement from youth outsend youth talks and final 100% swhen we have sister led sessions as well
YES | Bi-monthly events to attract youth | Higher engagement & building youth connection to masjid | Ad-hoc events running currently | Youth | End of March End of June End of Sept | Afsor | High | High | 2026-03-31 | Plan and deliver fortnightly events, social, Islamic, food etc for specific youth demographics | 24 | 2 every month | on-going | While this is aspiration. For youth, possible. We will continue with consistency on boys and girls circles. For the YA, we want to build more on providing experiences e.g. hike at seven sisters etc. Build stronger bonds + friendships. This helps them feel more connected to the mosque and the community. | In Progress |  | 50% | Q1: Ideas being progress: Experienced based events. Volunteering. DoE - our first volunteer. Building plans. Q2: Summer will be key. Where we want to get more volunteers and more experiences for youth.
YES | Leadership development | Safer, more competent teams | No formal youth leadership structure; involvement is ad‑hoc and reactive | OPEX | End of March End of June End of Sept | Amer | Low | Medium | 2026-03-31 | Training calendar (safeguarding, first aid, comms) | 1 | Book trainers; certificates; track completion | 18.01.26 | Begin leadership development programme with Yusra training | In Progress | Completion of pre-training 1-2-1 sessions with OPEX | 70% | Youth Lead Afsor Miah is captured within this training programme. Following MOSCARS awards ceremony several youth volunteers were identified for consideration for a youth council or shadow trustee/directors board. Shaffiq has put document tyogether detailing proposed structure. Some of the youth m,embers have also attended Yusar training sessions.
YES | Leadership development | Pipeline of young leaders, succession planning | Scouts provision low | Scouts | End of March End of June End of Sept | Khaleeq | Medium | Medium | 2026-03-31 | Increase number of Scouts places- key issue; staffing | 1 | Increase staff numbers | 31.01.26 | Advertising targeted for Q1. Story around impact and outcomes. We will keep on top of this. We will review impact. | Not Started |  | 0% | Risk: Scout leader is leaving. Need to first onboard a new lead Lack of volunteers are we progressing this?

## Wider Community Engagement
ULTIMATE AIM : BUILD BENEFICIAL PARTNERSHIPS SLT - Lead Matiur | [9 empty] | Wider Community Engagement
IS VALID | SMART Outcome | Benefit | Starting Point / Baseline | Department | Reported to OPEX | Responsible Person | Risk Level | Risk if Not Achieved | Target Date | Specific Desired Outcome | Milestone Count | Milestone/s | Milestone/s Date | Actions | Status | Reason for Delay | Complete % | Notes
YES | Build partnerships | Shared impact & credibility, improved societal integration | 3–4 informal partnerships; sporadic open days; no structured annual calendar | Community / Politics | End of March End of June End of Sept | Matiur | Medium | High | 2026-05-31 | Sign 5 MOUs with local orgs | 3 | 1. Target list (schools, council, charities); template MOU 2. Set up Bromley Citizens UK 3. Recruit more volunteers for Citizens UK | 1. Apr 2. Sept 3. Feb | Further Citizen's UK meeting attended by other community members | In Progress |  | 40% | Founding Assembly of Bromley Citizens to be held on 30th April
YES | Community events | Improved public perception and relationships, increased local impact | 3–4 informal partnerships; sporadic open days; no structured annual calendar | Community / Politics | End of March End of June End of Sept | Avais | Medium | Medium | 2026-09-30 | Deliver 4 open community events | 5 | Plan calendar; steward training; inclusive themes. Include neighbourhood consultation (first build relationships, then ask what are your needs?)and Interfaith iftar | Feb - Calendar May - Eid Jun - World Cup Sep - Dec - Christmas | Online community Calendar is ready for Ramadan! Build an informal way of engaging with the mosque space to make it more accessiable for non muslims. Event invitations to consider non-muslim community. Partnerships - tbc | In Progress |  | 50% | Calendar up and running. Testing during Ramdan. Avais and Meryem to own, keep up to date. Need to make this calendar more avalaible to non muslim community. Coffee Cart super successful, we need to get someone to own this and also this need sto beome a more regular daily service. Q2: Progressing well. Eid event we invited wider community. I am keen to do an Art event, farmers market in August etc
YES | Transparency | Evidence for funders & partners | 3–4 informal partnerships; sporadic open days; no structured annual calendar | Community / Politics | End of March End of June End of Sept | Avais | Low | Medium | 2026-09-30 | Publish annual Community Impact Report | 3 | Collect metrics; case studies; design & print | On-going | Ensuring data capturing of events is requested before events. Looking to get more youth to take videos/photos during evets | Complete |  | 100% | We are getting data for events every time which is good, succewss is shared throguh leads utd, and we are keeping each other updated. Good progress on this and its linked well to marketing
YES | Non-Muslims understand Islam | Spreading the Deen and benefitting local community. Islamic stereotypes broken | Recruited da'ee group; completing training. Dawah stall equipment and clothing being sourced, branding complete. Awaiting stall permission from Bromley Council | Religious Affairs | End of March End of June End of Sept | Ahmed | Low | Medium | 2026-01-31 | Live, active Da'wah project | 3 | 1. Complete purchases of equipment 2. Stall permission granted 3. Volunteer training complete | 1. Jan end 2. Jan end 3. Jan end |  | In Progress |  | 90%
YES | Engage and connect with local schools and scouts groups | Active daw'ah and increasing Islamic knowledge (including breaking stereotypes) of young local people through immersive experiences | School and scouts visits service already active, through school/scout group contact | Education | End of March End of June End of Sept | Sobia | Low | Medium | 2026-05-31 | Service to become proactive, reaching out to schools /scout groups | 6 | 1. Attract and retain further volunteers 2. Begin actively reaching out to schools/scout groups 3. Engage Bromley College 4. Invite them to our wider events 5. Get them to partake in our Ramadhan Challenge and iftars | 1. Jan Mid 2. May End 3. Feb End 4. Feb Begin 5. Feb end | Successfully attracted and retained additional volunteers to support the mosque visits programme. | In Progress |  | 50%
YES | Deepen relationships and benefit from connections to other faiths | Learn from them, teach them about Islam, break stereotypes, aid geo/political dialogues/situations | Already esablished long term Interfaith relationships | Education | End of March End of June End of Sept | Sofi | Medium | High | 2026-09-15 | Participate in regular Interfaith meetings and continue to educate about Islam, lessons learned from our shared prophets and highlight the advantages of being a people of peace who pray, fast and are ready to help others | 3 | 1. Get more of our community involved 2. Strengthen relationships with focus on Justice 3. Benefit from learning about how other faiths function,e.g. financial set up of Christians, power dynamics from Jews. 4.Plan Islamophobia and anti-semitism workshops | 1. Feb end 2. Apr end 3. Sep end | 1. Work in progress re drawing more of our community . Issues are due to advertising events late, this is partly due to the sensitive nature of the topics and have been hesitant to advertise. 2 | In Progress |  | 50%
YES | Connect with, market, and advertise well with wider community | Improved community cohesion | Have an existing but out of date and non searchable database. A sharepoint version now exists in SharePoint | Community / Politics | End of March End of June End of Sept | Matiur | Medium | Medium | 2026-07-31 | Build useful, searchable, regularly updated database of community contacts | 1 |  |  |  | In Progress |  | 10% | To be reviewed after Eid. Interfaith iftar invitations was not well executed with many key stakeholders missed
Work in progress:
5) Ramadan challenge & iftar
•

## Building Teams & Leadership
ULTIMATE AIM : DEVELOP LEADERSHIP TEAMS, ESPECIALLY VOLUNTEERS SLT Lead Amer | [9 empty] | Building Teams & Leadership
IS VALID | SMART Outcome | Benefit | Starting Point / Baseline | Department | Reported to OPEX | Responsible Person | Risk Level | Risk if Not Achieved | Target Date | Specific Desired Outcome | Milestone Count | Milestone/s | Milestone/s Date | Actions | Status | Reason for Delay | Complete % | Notes
YES | Competence & compliance | Risk reduction; improved leadership | Partial ad-hoc training coverage | OPEX | End of March End of June End of Sept | Amer | Medium | High | 2026-06-30 | Train all leads in leadership, governance & safeguarding | 1 | Book courses; track completion | Yusra training starting 18/01/26 | Leasdership development programme 8 half day sessions over 6-12 months | In Progress |  | 60% | To reconvene after Ramadan. Traing resumed Fri 1st May. However poor attendance (6 delegetes) Agreed with trainer Shahid to consider hybrid delivery of next session to encourage more attendees. Online Zoom training delivered Sat 20th June successfully with 2 attendees including most Leads and some team members. Good feedback and training well received. Will speak to Shahid at Yusra training to see how this can be delivered for the remaining sessions. Recent online scheduled session July 18th postponed as trainer's wife unwell. To re-organise.
YES | Onboarding excellence | Faster integration; safety | Onboarding is informal | OPEX | End of March End of June End of Sept | Amer | Low | Medium | 2026-04-30 | Structured induction pack and build a process to align volunteers to roles | 5 | Checklist; DBS; H&S; first aid; handbook | Will need to liase with Ali to organise DBS, 1st Aid and staff handbook | No communication from Ali regarding staff handbook | In Progress | Ali has already DBS several leads. | 30% | Faridah has notified me of her stepping down from AEC duties including OPEX and Leads Utd from 30th March. Conversation with Shaffiq regarding Perkbox. Have messaged Br Behzat with proposal and is being considered. After further discussion, Perkbox has been parked as not enough interest generated for this platform. Flick still to be considered for recording of volunteer training and documentation. Spoken to Ali rearding taking over the helm of Leads Utd. Ali has now led a couple of meetings asking for monthly updates from the leads. Amer will coninue leading OPEX onboarding volunteers and organising training.
YES | Volunteer attraction and retention | Staff retention & morale | Volunteers praised by Leaders, Volunteer yearly event | OPEX | End of March End of June End of Sept | Amer | Medium | High | 2026-01-31 | Volunteer recognition & retention programme. considering Perkbox and other reward schemes. | 3 | Badges/PerkBox Dinner/awards; Yusra training | 1.Training starting 18.01.26 2. volunteer dinner to be arranged post ramadan 01.04.26 3. Badges/lanyards 30.03.26 | Amer to arrange sponsors and speakers for post Ramadan volunteer dinner as per last year. Following a thank you dinner at AEC arranged by Shaffiq and Shazli, I have separated the Leads award ceremony into the 'MOscars' to be held in the first week in April or first week of June. Families of leads to also be invited to acknowledge their support in the process. | In Progress | We did see some new voliunteers sign up at Ramadan but these were drated in the 'Ramadan group' headed by Br Tauffique and Br Shazli who are notably not part of Leads Utd and contunues to be a bone of contention. | 80% | sponsors to include Abrahams, Cuppa Chai, Langthorne Pharmacy, Garden Square Denta, Kayi Crossfit. MOSCARS Lead Volunteer awards ceremony delivered successfully. Some excellent feedback from this especially with encoragement for youth memebers. Consideration for these youth members to form a youth council or shadow directors committee. Afsor has stepped back from youth activitie for now due to personal reasons. Will need to organise youth board meeting.
YES | Improved performance in key areas | Make important functions work better, prevent burnout | Digital, Marketing and Outreach teams limited human resources | OPEX | End of March End of June End of Sept | Amer | High | High | 2026-06-30 | Increase volunteers in Digital, Marketing and Outreach Teams | 3 | Role profiles; mentoring; appraisal process | Volunteer drive during Ramadan | Request Imam to advertise volunteer rercuitment during Ramadan | In Progress | Imam has his own ideasabout volunteer training. He has run some Zoom online training session pre-Ramadan. | 50% | Imam Ossama had mentioned volunteers for Ramadan at Jummah Khutbah . After the departure of Imam Ossama we have not as yet led a volunteer drive but individiual gropups are reaching out to theoir own networks to recruit eg dawah project Ahmed Rawi. Still need top recruit further for SEND Tech team, and Scouts following imminent departure of Saira who is currently Lead.

## Community Activities
ULTIMATE AIM : DEVELOP A VIBRANT CALENDAR OF ENGAGING EVENTS, GROW ATTENDANCE + VOLUNTEER APPRECIATION SLT Lead Avais | [9 empty] | Community Activities
IS VALID | SMART Outcome | Benefit | Starting Point / Baseline | Department | Reported to OPEX | Responsible Person | Risk Level | Risk if Not Achieved | Target Date | Specific Desired Outcome | Milestone Count | Milestone/s | Milestone/s Date | Actions | Status | Reason for Delay | Complete % | Notes
YES | Vibrant Events Calendar | Cohesion & visibility | Approx. 6 activities per year; decentralised planning; limited follow-up/feedback loops | Events | End of March End of June End of Sept | Avais | Medium | Medium | 2026-09-30 | Deliver 10 high-impact events. Quarterly themes; partnerships; family focus | 6 | Big ticket events: Community and Neighbour Consultations, Eids,Volunteer thank you, Mosque Fayre, family BBQ, talks. Communicate these through calendar, newsletters and Annual Report |  |  | In Progress |  | 70% | Events wise, structure, lot of good things. Big community events we need to now plan post ramadan.
YES | Attendance growth | Broader engagement | Approx. 6 activities per year; decentralised planning; limited follow-up/feedback loops | Marketing | End of March End of June End of Sept | Ameera | Medium | Medium | 2026-09-30 | Strengthen visibility and engagement of community activities via social media and WhatsApp, contributing to at least a 25% increase in event attendance vs 2025 baseline | 3 | 1. Coordinated social media & WhatsApp promotion for all major community events. 2. Published and regularly updated community events calendar (online and/or on-site). 3. Systematic post-event feedback and attendance tracking after major events. | Jan 2026: Initial coordinated promotion in place + draft calendar created. Feb 2026: Online calendar live and used for Ramadan communications. Jun 2026: Regular promotion embedded + feedback piloted. Sept 2026: Approach fully embedded with systematic feedback and attendance tracking. | Work with the Events Team to coordinate promotion of major community activities via social media and WhatsApp; work with the Digital Team to maintain an up-to-date online events calendar; and support the rollout of simple post-event feedback and attendance tracking. | In Progress |  | 70% | Ramadan programme successfully delivered with very strong attendance and engagement; mosque consistently full across key events. Coordinated promotion via WhatsApp and social media, supported by live events calendar. Positive feedback and compliments received from the community
YES | Events well advertised and attended | Increased event attendance,staff booking system | No calendar currently available | Tech | End of March End of June End of Sept | Khaleeq | High | High | 2026-05-31 | Clear electronic calendar of events for staff and community to see/access | 3 | 1. Set up calendars 2. Integrate 3. Share | 1. Jan 2.Jan 3. Feb |  | In Progress |  | 70%

## Spiritual Focus
ULTIMATE AIM : COMMUNITY TRANSFORMATION SLT Lead Omar Taha | [9 empty] | Spiritual Focus
IS VALID | SMART Outcome | Benefit | Starting Point / Baseline | Department | Reported to OPEX | Responsible Person | Risk Level | Risk if Not Achieved | Target Date | Specific Desired Outcome | Milestone Count | Milestone/s | Milestone/s Date | Actions | Status | Reason for Delay | Complete % | Notes
YES | Learning & practice | Deeper community spirituality | Regular Jumu’ah/Ramadan programmes; limited modular learning beyond madrassa/occasional talks | Islamic Affairs | End of March End of June End of Sept | Omar | Medium | Medium | 2026-09-30 | Increase participation in structured spiritual education by 30% by September 2026. | 3 | 1. Modular spiritual education courses introduced beyond Jumu’ah and Ramadan. 2. Family-friendly timings implemented to widen access to learning programmes. | Jan 2026: Pilot modular spiritual education sessions (including Ramadan programmes). Jun 2026: Regular modular courses running with family-friendly timings. Sept 2026: Programme fully embedded with sustained and increased attendance. | Develop and deliver modular spiritual education programmes, building on existing classes and talks; introduce family-friendly timings and expand engagement with youth, children, and reverts. | In Progress |  | 90% | 1. Weekly tafsir started June for all members of family 2. Sisters fortnightly halaqah started. 3. Youth 16-25 circle for men started. 4. Youth monthly q&a started. 5. Youth Rawa tales planned in June 6. Fajr club felt covers brothers circle 7. Guest khateebs Sh Ziyad and Sh Zubayr 8. Completed Ramadan and Dhul Hijjah social media reminders 9. In need of revert, youth sisters and 11-15 brothers 10. Possibly an Isha reminder (more appropriate for Imam)
YES | Learning & practice | Deeper community spirituality | Limited talks to date | Islamic Affairs | End of March End of June End of Sept | Omar | Medium | Medium | 2026-09-30 | Deliver a consistent programme of small and large-scale talks for diverse demographics to increase engagement and spiritual understanding by September 2026. | 4 | 1. Monthly themed talks delivered for key demographics. 2. Guest speakers introduced for selected sessions. 3. Increased attendance and engagement across talk programmes. | Jan 2026: Monthly talk structure established Jun 2026: Guest speakers and varied topics introduced Sept 2026: Programme embedded with strong attendance | Plan and deliver regular talks across different demographics, including khutbahs, short reminders, and guest sessions, to increase engagement and accessibility. | In Progress |  | 60% | 1. Plan for September Ilm Essentials 1 year programme 2. Plan for Tajweed for ladies Sep and for Arabic ladies tajweed 3. Seeking a lead for Arabic and men's tajweed 4. Agreed regular marriage related talks 5. History talk 21st June 6. Planning riba talk with Ustadh Umer Sulaiman 7. Completed Ramadan and Hajj talks 8. Planning Mothers Quran group 9. Aim Khutbah delivery workshop by Sep 10. Planning a sisters q&a (either Omar or Imam) 11. Planning hifdh programme (Imam)
YES | Al-Qalam Madrassa expansion | Education for young people in our community, development fo youth leaders | Already have an established Madrassa | Education | End of March End of June End of Sept | Omar | Medium | Medium | 2026-09-30 | Increase student numbers whilst maintaining educational standards | 1 | 1. New leadership team settled into roles 2. Move to Ravenswood secured by June 2026 | 1. End of March 2. End of June |  | In Progress |  | 80% | Ravenswood move complete! Curriculum has been proposed, and being finalised. Omar to plan a meeting with teachers on this. Leadership team better place than last year, appears to have worked. Awaiting full report by next month. Awaiting open day and review of numbers in coming month.
YES | Community retreats | Renewal & connection | Limited spiritual development to date | Islamic Affairs | End of March End of June End of Sept | Omar | Medium | Medium | 2026-08-31 | Deliver quarterly spiritual retreats and Qur’an reflection circles to strengthen community connection and spiritual growth by August 2026. | 3 | 1. Retreat structure and programme designed (including Qur’an reflection focus). 2. Logistics in place (venue, childcare, sign-ups). 3. First retreat delivered and model refined for ongoing quarterly delivery. | Jan 2026: Retreat format and programme agreed. Jun 2026: First retreat delivered with logistics in place. Aug 2026: Quarterly retreat model embedded. | Plan and deliver quarterly retreats including Qur’an reflection sessions, ensuring accessibility through childcare and structured sign-up processes. | In Progress |  | 30% | To consider embedding into camp retreat, or considering a youth excurcusion with reminders. Not yet ready for full education retreat given my time committments - potentially one for an incoming Imam
YES | Spiritual self- development | Deeper individual spirituality | Not formally developed | Exec | End of March End of June End of Sept | Shaffiq | Medium | Medium | 2026-09-30 | A system which allows individual community members to begin a tracked, AI driven,journey starting from where they are, built upon the resources available at the masjid. Includes training, courses and volunteering | 2 | 1. Get MosqueApp running 2. Develop and deploy framework for personal self-development | 1. Jan 2. Before Ramadhan | Found possible suitable provider. had second round meetings with him. Next steps: asked him for a one pager explaining his product, a one pager for my Education Lead, detailing Islamic education authenticity, and then we will meet to finalise the financials and how that works, and how to embed the product via ai to our masjid, its services, volunteering etc. Decided to launch via our website and not wait until app is completed. | Delayed |  | 60% | Need Khalyfa guy to produce scholar endorsement and fine checking for educational content before we proceed any further

## Data (Master Table)
MASTER KEY | Focus Area | IS VALID | SMART Outcome | Benefit | Starting Point / Baseline | Department | Reported to OPEX | Responsible Person | Risk Level | Risk if Not Achieved | Target Date | Specific Desired Outcome | Milestone Count | Milestone/s | Milestone/s Date | Actions | Status | Reason for Delay | Complete % | Notes | FOCUS AREA LIST | PROGRESS LIST | COMPLETION LIST | RISK | IS VALID
FS1 | Financial Stability | YES | Establish diversified, sustainable income streams | Service provision, significant income stream to be invested in Waqf | Donation-dependent operations; limited reserves; no diversified income operational yet. Soft launch of TFS complete | Safa Holdings / Finance | End of March End of June End of Sept | Shaffiq | Medium | High | 2026-02-28 | Deliver a live Funeral Service: Tahreem Funeral Service (operational & marketed) | 3 | 1. Cement policies & procedures 2. Hard Launch 3. Full service provision + £ | 1. Jan - March 2. March 3. Mar - Sept | Continuous service improvement, additional fridge set up. Imam and Funeral Director to run roadshow prior to hard launch. Thorough marketing and relationship building- cemeteries, hospitals etc. Add our website link to other masajid and Eternal Gardens website | Complete |  | 100% | The launch included delivering 21 full funerals, tightening policies and procedures, adding fridges, creating leaflets, livening the website, sending emails and WhatsApp messages, building relationships with Shirley, Penge, Purley, MCWAS, Tunbridge Wells and Maidstone (including use of facilities at Maidstone and TW). Send messages to our community, making a popup for the AEC website, setting up Tahreem@group email, adding our details to the Eternal Gardens website, announcing at jumu'ah. Before hard laucnh we have made a net profit of £20k | Financial Stability | Not Started | 0% | High | YES
FS2 | Financial Stability | YES | Establish diversified, sustainable income streams | Service provision, recurring advertising revenue + partnerships | Donation-dependent operations; limited reserves; no diversified income operational yet. Idea and website ready for Business Directory | Safa Holdings / Finance | End of March End of June End of Sept | Raja | Medium | Medium | 2026-03-31 | Launch Green Pages Business Directory (100+ listings.) Launch through MosqueApp | 1 | Created website offering, Raja to launch and do intital pre registration checks | 2026-04-30 | Intro offer; outreach to local businesses; simple sign-up | In Progress |  | 90% | Raja is on this iA | Youth Succession Planning | In Progress | 10% | Medium | NO
FS3 | Financial Stability | NO | Grow current Waqf capital by £60,000 by Sept 2026 | Perpetual income for AEC | Donation-dependent operations; limited reserves; no diversified income operational yet. Curently contains £75k | Finance | End of March End of June End of Sept | Raja / Kamraan | Low | High | 2026-06-30 | Raise £60k additional funds for waqf investment |  | Ramadhan Waqf fundraising round 2 | Last 10 days of Ramadhan | Friday talks, create deck for last 10 days of Ramadhan | In Progress | The amount we wanted to raise in the last 10 days of Ramadhan was not realised |  | Will look to HNW network to achieve this | Wider Community Engagement | Complete | 20% | Low
FS4 | Financial Stability | YES | Grow Waqf capital to £200,000 by Sept 2026 | Step-change in waqf investment amount | Donation-dependent operations; limited reserves; no diversified income operational yet. Curently contains £75k (+£60k Ramadhan iA) | Exec | End of March End of June End of Sept | Shaffiq | Medium | High | 2026-09-30 | Increase waqf investment by further £65k | 1 | HNW and individual investor approach pack + roadshows | 2026-09-01 | Curated deck; Brunei / Malaysian network, donor lunches; targeted HNW outreach | In Progress |  | 70% |  | Building Teams & Leadership | Delayed | 30%
FS5 | Financial Stability | YES | Achieve net-positive operating balance by Sept 2026 | Operational transparency + sustainability | Donation-dependent operations; limited reserves; no diversified income operational yet | Finance | End of March End of June End of Sept | Behzat / Raja / Kamraan | Low | Medium | 2026-09-30 | Monthly finance dashboard & cost controls | 1 | Ramadhan BAU fundraising Dashboard creation | 2026-09-01 | Budget discipline; procurement policy | In Progress |  | 0% |  | Community Activities |  | 40%
FS6 | [20 empty] | Spiritual Focus |  | 50%
FS7 | [22 empty] | 60%
FS8 | [22 empty] | 70%
FS9 | [22 empty] | 80%
FS10 | [22 empty] | 90%
FS11 | [22 empty] | 100%
FS12
FS13
FS14
FS15
YS1 | Youth Succession Planning | YES | Develop youth leadership | Pipeline of young leaders, succession planning | No formal youth leadership structure; involvement is ad‑hoc and reactive | Youth | End of March End of June End of Sept | Afsor | Medium | High | 2026-02-15 | Establish Youth Council (10 members) + Shadow Trustees + Key staff positions proteges allocated | 1 | Clear roles; mentor pairing; monthly meetings, Liaise with Madrassa, Scouts, Boxing and Taekwondo functions | Target end Ramadan for first results | Ramadan: Volunteer Request, Omar Youth talks > key to identify youth. Youth Experience event plan for post Ramadan. | In Progress |  | 80% | Results Ramadan> Youth activiites - building responsibility for the youth across the mosque. Demonstrated across youth events, running the coffee cart (i.e not just running, but also increasing product range to generate more "revenue" for the mosque), youth volunteers. How does this line with pipelne of young leaders: We have identified young leaders who we would recommend as part of a youth leadership strucutre that can support our growth. So based on we have identnfied caditates and now its about setting the strucutre, we have completed 40%, next 20% is setting structure, next 20% is executing it, and final 20% is ensuring its operating as part of the wider management teams. Q2: setting up youth board in progress.
YS2 | Youth Succession Planning | YES | Increase youth volunteering team by 40% | Higher engagement & continuity | Current team number: X | Youth | End of March End of June End of Sept | Afsor | Low | Medium | 2026-06-30 | Quarterly youth volunteer drives | 1 | School/college outreach; buddy system | Target end Ramadan for first results | Ramadan - youth voltuneering kicked off. | In Progress |  | 60% | Q1:Results Ramadan: Youth volunteering from our advertising was not as successful but we had youth volunteering more by supporting the young adults i.e. Davids kids were helping coffee stand. We just need a bit more forward planning around youth volunteer requirements leading up to events, lead with young adults .. this will yield better results in future. Q2: We are building a core set of youth who are very engaged. Summer will be an important time to build events which bring our youth together.
YS3 | Youth Succession Planning | YES | Targeted talks to attract youth | Higher engagement & building youth connection to masjid | Ad-hoc talks currently | Youth | End of March End of June End of Sept | Afsor | Medium | Medium | 2026-03-31 | Plan and deliver targeted talks for all youth demographics | 6 | 1 every 2 months | Target end Ramadan for first results | Working with Omar to create a better set of talks for youth. Focus is not purley on topic, but more on connecting them to mentors + people they can respect/look up too (people who are not to old). First test of this will be in Ramadan. | In Progress |  | 60% | Ramadan Resulst > Continue youth. Omar and Eni doing a great job. Think we need a sisters lead one switch at some point. 60% completion rate once we get consisten cy, have new people joining, 80% once we see engagement from youth outsend youth talks and final 100% swhen we have sister led sessions as well
YS4 | Youth Succession Planning | YES | Bi-monthly events to attract youth | Higher engagement & building youth connection to masjid | Ad-hoc events running currently | Youth | End of March End of June End of Sept | Afsor | High | High | 2026-03-31 | Plan and deliver fortnightly events, social, Islamic, food etc for specific youth demographics | 24 | 2 every month | on-going | While this is aspiration. For youth, possible. We will continue with consistency on boys and girls circles. For the YA, we want to build more on providing experiences e.g. hike at seven sisters etc. Build stronger bonds + friendships. This helps them feel more connected to the mosque and the community. | In Progress |  | 50% | Q1: Ideas being progress: Experienced based events. Volunteering. DoE - our first volunteer. Building plans. Q2: Summer will be key. Where we want to get more volunteers and more experiences for youth.
YS5 | Youth Succession Planning | YES | Leadership development | Safer, more competent teams | No formal youth leadership structure; involvement is ad‑hoc and reactive | OPEX | End of March End of June End of Sept | Amer | Low | Medium | 2026-03-31 | Training calendar (safeguarding, first aid, comms) | 1 | Book trainers; certificates; track completion | 18.01.26 | Begin leadership development programme with Yusra training | In Progress | Completion of pre-training 1-2-1 sessions with OPEX | 70% | Youth Lead Afsor Miah is captured within this training programme. Following MOSCARS awards ceremony several youth volunteers were identified for consideration for a youth council or shadow trustee/directors board. Shaffiq has put document tyogether detailing proposed structure. Some of the youth m,embers have also attended Yusar training sessions.
YS6 | Youth Succession Planning | YES | Leadership development | Pipeline of young leaders, succession planning | Scouts provision low | Scouts | End of March End of June End of Sept | Khaleeq | Medium | Medium | 2026-03-31 | Increase number of Scouts places- key issue; staffing | 1 | Increase staff numbers | 31.01.26 | Advertising targeted for Q1. Story around impact and outcomes. We will keep on top of this. We will review impact. | Not Started |  | 0% | Risk: Scout leader is leaving. Need to first onboard a new lead Lack of volunteers are we progressing this?
YS7
YS8
YS9
YS10
YS11
YS12
YS13
YS14
YS15
WC1 | Wider Community Engagement | YES | Build partnerships | Shared impact & credibility, improved societal integration | 3–4 informal partnerships; sporadic open days; no structured annual calendar | Community / Politics | End of March End of June End of Sept | Matiur | Medium | High | 2026-05-31 | Sign 5 MOUs with local orgs | 3 | 1. Target list (schools, council, charities); template MOU 2. Set up Bromley Citizens UK 3. Recruit more volunteers for Citizens UK | 1. Apr 2. Sept 3. Feb | Further Citizen's UK meeting attended by other community members | In Progress |  | 40% | Calendar up and running. Testing during Ramdan. Avais and Meryem to own, keep up to date. Need to make this calendar more avalaible to non muslim community. Coffee Cart super successful, we need to get someone to own this and also this need sto beome a more regular daily service. Q2: Progressing well. Eid event we invited wider community. I am keen to do an Art event, farmers market in August etc
WC2 | Wider Community Engagement | YES | Community events | Improved public perception and relationships, increased local impact | 3–4 informal partnerships; sporadic open days; no structured annual calendar | Community / Politics | End of March End of June End of Sept | Avais | Medium | Medium | 2026-09-30 | Deliver 4 open community events | 5 | Plan calendar; steward training; inclusive themes. Include neighbourhood consultation (first build relationships, then ask what are your needs?)and Interfaith iftar | Feb - Calendar May - Eid Jun - World Cup Sep - Dec - Christmas | Online community Calendar is ready for Ramadan! Build an informal way of engaging with the mosque space to make it more accessiable for non muslims. Event invitations to consider non-muslim community. Partnerships - tbc | In Progress |  | 50% | #REF!
WC3 | Wider Community Engagement | YES | Transparency | Evidence for funders & partners | 3–4 informal partnerships; sporadic open days; no structured annual calendar | Community / Politics | End of March End of June End of Sept | Avais | Low | Medium | 2026-09-30 | Publish annual Community Impact Report | 3 | Collect metrics; case studies; design & print | On-going | Ensuring data capturing of events is requested before events. Looking to get more youth to take videos/photos during evets | Complete |  | 100% | We are getting data for events every time which is good, succewss is shared throguh leads utd, and we are keeping each other updated. Good progress on this and its linked well to marketing
WC4 | Wider Community Engagement | YES | Non-Muslims understand Islam | Spreading the Deen and benefitting local community. Islamic stereotypes broken | Recruited da'ee group; completing training. Dawah stall equipment and clothing being sourced, branding complete. Awaiting stall permission from Bromley Council | Religious Affairs | End of March End of June End of Sept | Ahmed | Low | Medium | 2026-01-31 | Live, active Da'wah project | 3 | 1. Complete purchases of equipment 2. Stall permission granted 3. Volunteer training complete | 1. Jan end 2. Jan end 3. Jan end |  | In Progress |  | 90%
WC5 | Wider Community Engagement | YES | Engage and connect with local schools and scouts groups | Active daw'ah and increasing Islamic knowledge (including breaking stereotypes) of young local people through immersive experiences | School and scouts visits service already active, through school/scout group contact | Education | End of March End of June End of Sept | Sobia | Low | Medium | 2026-05-31 | Service to become proactive, reaching out to schools /scout groups | 6 | 1. Attract and retain further volunteers 2. Begin actively reaching out to schools/scout groups 3. Engage Bromley College 4. Invite them to our wider events 5. Get them to partake in our Ramadhan Challenge and iftars | 1. Jan Mid 2. May End 3. Feb End 4. Feb Begin 5. Feb end | Successfully attracted and retained additional volunteers to support the mosque visits programme. | In Progress |  | 50%
WC6 | Wider Community Engagement | YES | Deepen relationships and benefit from connections to other faiths | Learn from them, teach them about Islam, break stereotypes, aid geo/political dialogues/situations | Already esablished long term Interfaith relationships | Education | End of March End of June End of Sept | Sofi | Medium | High | 2026-09-15 | Participate in regular Interfaith meetings and continue to educate about Islam, lessons learned from our shared prophets and highlight the advantages of being a people of peace who pray, fast and are ready to help others | 3 | 1. Get more of our community involved 2. Strengthen relationships with focus on Justice 3. Benefit from learning about how other faiths function,e.g. financial set up of Christians, power dynamics from Jews. 4.Plan Islamophobia and anti-semitism workshops | 1. Feb end 2. Apr end 3. Sep end | 1. Work in progress re drawing more of our community . Issues are due to advertising events late, this is partly due to the sensitive nature of the topics and have been hesitant to advertise. 2 | In Progress |  | 50%
WC7 | Wider Community Engagement | YES | Connect with, market, and advertise well with wider community | Improved community cohesion | Have an existing but out of date and non searchable database. A sharepoint version now exists in SharePoint | Community / Politics | End of March End of June End of Sept | Matiur | Medium | Medium | 2026-07-31 | Build useful, searchable, regularly updated database of community contacts | 1 |  |  |  | In Progress |  | 10% | To be reviewed after Eid. Interfaith iftar invitations was not well executed with many key stakeholders missed
WC8 | [15 empty] | Work in progress:
WC9
WC10
WC11
WC12
WC13
WC14
WC15
BT1 | Building Teams & Leadership | YES | Competence & compliance | Risk reduction; improved leadership | Partial ad-hoc training coverage | OPEX | End of March End of June End of Sept | Amer | Medium | High | 2026-06-30 | Train all leads in leadership, governance & safeguarding | 1 | Book courses; track completion | Yusra training starting 18/01/26 | Leasdership development programme 8 half day sessions over 6-12 months | In Progress |  | 60% | To reconvene after Ramadan. Traing resumed Fri 1st May. However poor attendance (6 delegetes) Agreed with trainer Shahid to consider hybrid delivery of next session to encourage more attendees. Online Zoom training delivered Sat 20th June successfully with 2 attendees including most Leads and some team members. Good feedback and training well received. Will speak to Shahid at Yusra training to see how this can be delivered for the remaining sessions. Recent online scheduled session July 18th postponed as trainer's wife unwell. To re-organise.
BT2 | Building Teams & Leadership | YES | Onboarding excellence | Faster integration; safety | Onboarding is informal | OPEX | End of March End of June End of Sept | Amer | Low | Medium | 2026-04-30 | Structured induction pack and build a process to align volunteers to roles | 5 | Checklist; DBS; H&S; first aid; handbook | Will need to liase with Ali to organise DBS, 1st Aid and staff handbook | No communication from Ali regarding staff handbook | In Progress | Ali has already DBS several leads. | 30% | Faridah has notified me of her stepping down from AEC duties including OPEX and Leads Utd from 30th March. Conversation with Shaffiq regarding Perkbox. Have messaged Br Behzat with proposal and is being considered. After further discussion, Perkbox has been parked as not enough interest generated for this platform. Flick still to be considered for recording of volunteer training and documentation. Spoken to Ali rearding taking over the helm of Leads Utd. Ali has now led a couple of meetings asking for monthly updates from the leads. Amer will coninue leading OPEX onboarding volunteers and organising training.
BT3 | Building Teams & Leadership | YES | Volunteer attraction and retention | Staff retention & morale | Volunteers praised by Leaders, Volunteer yearly event | OPEX | End of March End of June End of Sept | Amer | Medium | High | 2026-01-31 | Volunteer recognition & retention programme. considering Perkbox and other reward schemes. | 3 | Badges/PerkBox Dinner/awards; Yusra training | 1.Training starting 18.01.26 2. volunteer dinner to be arranged post ramadan 01.04.26 3. Badges/lanyards 30.03.26 | Amer to arrange sponsors and speakers for post Ramadan volunteer dinner as per last year. Following a thank you dinner at AEC arranged by Shaffiq and Shazli, I have separated the Leads award ceremony into the 'MOscars' to be held in the first week in April or first week of June. Families of leads to also be invited to acknowledge their support in the process. | In Progress | We did see some new voliunteers sign up at Ramadan but these were drated in the 'Ramadan group' headed by Br Tauffique and Br Shazli who are notably not part of Leads Utd and contunues to be a bone of contention. | 80% | sponsors to include Abrahams, Cuppa Chai, Langthorne Pharmacy, Garden Square Denta, Kayi Crossfit. MOSCARS Lead Volunteer awards ceremony delivered successfully. Some excellent feedback from this especially with encoragement for youth memebers. Consideration for these youth members to form a youth council or shadow directors committee. Afsor has stepped back from youth activitie for now due to personal reasons. Will need to organise youth board meeting.
BT4 | Building Teams & Leadership | YES | Improved performance in key areas | Make important functions work better, prevent burnout | Digital, Marketing and Outreach teams limited human resources | OPEX | End of March End of June End of Sept | Amer | High | High | 2026-06-30 | Increase volunteers in Digital, Marketing and Outreach Teams | 3 | Role profiles; mentoring; appraisal process | Volunteer drive during Ramadan | Request Imam to advertise volunteer rercuitment during Ramadan | In Progress | Imam has his own ideasabout volunteer training. He has run some Zoom online training session pre-Ramadan. | 50% | Imam Ossama had mentioned volunteers for Ramadan at Jummah Khutbah . After the departure of Imam Ossama we have not as yet led a volunteer drive but individiual gropups are reaching out to theoir own networks to recruit eg dawah project Ahmed Rawi. Still need top recruit further for SEND Tech team, and Scouts following imminent departure of Saira who is currently Lead.
BT5
BT6
BT7
BT8
BT9
BT10
BT11
BT12
BT13
BT14
BT15
CA1 | Community Activities | YES | Vibrant Events Calendar | Cohesion & visibility | Approx. 6 activities per year; decentralised planning; limited follow-up/feedback loops | Events | End of March End of June End of Sept | Avais | Medium | Medium | 2026-09-30 | Deliver 10 high-impact events. Quarterly themes; partnerships; family focus | 6 | Big ticket events: Community and Neighbour Consultations, Eids,Volunteer thank you, Mosque Fayre, family BBQ, talks. Communicate these through calendar, newsletters and Annual Report |  |  | In Progress |  | 70% | Events wise, structure, lot of good things. Big community events we need to now plan post ramadan.
CA2 | Community Activities | YES | Attendance growth | Broader engagement | Approx. 6 activities per year; decentralised planning; limited follow-up/feedback loops | Marketing | End of March End of June End of Sept | Ameera | Medium | Medium | 2026-09-30 | Strengthen visibility and engagement of community activities via social media and WhatsApp, contributing to at least a 25% increase in event attendance vs 2025 baseline | 3 | 1. Coordinated social media & WhatsApp promotion for all major community events. 2. Published and regularly updated community events calendar (online and/or on-site). 3. Systematic post-event feedback and attendance tracking after major events. | Jan 2026: Initial coordinated promotion in place + draft calendar created. Feb 2026: Online calendar live and used for Ramadan communications. Jun 2026: Regular promotion embedded + feedback piloted. Sept 2026: Approach fully embedded with systematic feedback and attendance tracking. | Work with the Events Team to coordinate promotion of major community activities via social media and WhatsApp; work with the Digital Team to maintain an up-to-date online events calendar; and support the rollout of simple post-event feedback and attendance tracking. | In Progress |  | 70% | Ramadan programme successfully delivered with very strong attendance and engagement; mosque consistently full across key events. Coordinated promotion via WhatsApp and social media, supported by live events calendar. Positive feedback and compliments received from the community
CA3 | Community Activities | YES | Events well advertised and attended | Increased event attendance,staff booking system | No calendar currently available | Tech | End of March End of June End of Sept | Khaleeq | High | High | 2026-05-31 | Clear electronic calendar of events for staff and community to see/access | 3 | 1. Set up calendars 2. Integrate 3. Share | 1. Jan 2.Jan 3. Feb |  | In Progress |  | 70%
CA4
CA5
CA6
CA7
CA8
CA9
CA10
CA11
CA12
CA13
CA14
CA15
SF1 | Spiritual Focus | YES | Learning & practice | Deeper community spirituality | Regular Jumu’ah/Ramadan programmes; limited modular learning beyond madrassa/occasional talks | Islamic Affairs | End of March End of June End of Sept | Omar | Medium | Medium | 2026-09-30 | Increase participation in structured spiritual education by 30% by September 2026. | 3 | 1. Modular spiritual education courses introduced beyond Jumu’ah and Ramadan. 2. Family-friendly timings implemented to widen access to learning programmes. | Jan 2026: Pilot modular spiritual education sessions (including Ramadan programmes). Jun 2026: Regular modular courses running with family-friendly timings. Sept 2026: Programme fully embedded with sustained and increased attendance. | Develop and deliver modular spiritual education programmes, building on existing classes and talks; introduce family-friendly timings and expand engagement with youth, children, and reverts. | In Progress |  | 90% | 1. Weekly tafsir started June for all members of family 2. Sisters fortnightly halaqah started. 3. Youth 16-25 circle for men started. 4. Youth monthly q&a started. 5. Youth Rawa tales planned in June 6. Fajr club felt covers brothers circle 7. Guest khateebs Sh Ziyad and Sh Zubayr 8. Completed Ramadan and Dhul Hijjah social media reminders 9. In need of revert, youth sisters and 11-15 brothers 10. Possibly an Isha reminder (more appropriate for Imam)
SF2 | Spiritual Focus | YES | Regular themed lectures | Accessible Islamic education | Limited spiritual development to date | Education | End of March End of June End of Sept | Omar | Medium | Medium | 2026-04-30 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
SF3 | Spiritual Focus | YES | Community retreats | Renewal & connection | Limited spiritual development to date | Islamic Affairs | End of March End of June End of Sept | Omar | Medium | Medium | 2026-08-31 | Deliver quarterly spiritual retreats and Qur’an reflection circles to strengthen community connection and spiritual growth by August 2026. | 3 | 1. Retreat structure and programme designed (including Qur’an reflection focus). 2. Logistics in place (venue, childcare, sign-ups). 3. First retreat delivered and model refined for ongoing quarterly delivery. | Jan 2026: Retreat format and programme agreed. Jun 2026: First retreat delivered with logistics in place. Aug 2026: Quarterly retreat model embedded. | Plan and deliver quarterly retreats including Qur’an reflection sessions, ensuring accessibility through childcare and structured sign-up processes. | In Progress |  | 30% | To consider embedding into camp retreat, or considering a youth excurcusion with reminders. Not yet ready for full education retreat given my time committments - potentially one for an incoming Imam
SF4 | Spiritual Focus | YES | Al-Qalam Madrassa expansion | Education for young people in our community, development fo youth leaders | Already have an established Madrassa | Education | End of March End of June End of Sept | Omar | Medium | Medium | 2026-09-30 | Increase student numbers whilst maintaining educational standards | 1 | 1. New leadership team settled into roles 2. Move to Ravenswood secured by June 2026 | 1. End of March 2. End of June |  | In Progress |  | 80% | Ravenswood move complete! Curriculum has been proposed, and being finalised. Omar to plan a meeting with teachers on this. Leadership team better place than last year, appears to have worked. Awaiting full report by next month. Awaiting open day and review of numbers in coming month.
SF5 | Spiritual Focus | YES | Learning & practice | Deeper community spirituality | Limited talks to date | Islamic Affairs | End of March End of June End of Sept | Omar | Medium | Medium | 2026-09-30 | Deliver a consistent programme of small and large-scale talks for diverse demographics to increase engagement and spiritual understanding by September 2026. | 4 | 1. Monthly themed talks delivered for key demographics. 2. Guest speakers introduced for selected sessions. 3. Increased attendance and engagement across talk programmes. | Jan 2026: Monthly talk structure established Jun 2026: Guest speakers and varied topics introduced Sept 2026: Programme embedded with strong attendance | Plan and deliver regular talks across different demographics, including khutbahs, short reminders, and guest sessions, to increase engagement and accessibility. | In Progress |  | 60% | 1. Plan for September Ilm Essentials 1 year programme 2. Plan for Tajweed for ladies Sep and for Arabic ladies tajweed 3. Seeking a lead for Arabic and men's tajweed 4. Agreed regular marriage related talks 5. History talk 21st June 6. Planning riba talk with Ustadh Umer Sulaiman 7. Completed Ramadan and Hajj talks 8. Planning Mothers Quran group 9. Aim Khutbah delivery workshop by Sep 10. Planning a sisters q&a (either Omar or Imam) 11. Planning hifdh programme (Imam)
SF7 | Spiritual Focus | YES | Spiritual self- development | Deeper individual spirituality | Not formally developed | Exec | End of March End of June End of Sept | Shaffiq | Medium | Medium | 2026-09-30 | A system which allows individual community members to begin a tracked, AI driven,journey starting from where they are, built upon the resources available at the masjid. Includes training, courses and volunteering | 2 | 1. Get MosqueApp running 2. Develop and deploy framework for personal self-development | 1. Jan 2. Before Ramadhan | Found possible suitable provider. had second round meetings with him. Next steps: asked him for a one pager explaining his product, a one pager for my Education Lead, detailing Islamic education authenticity, and then we will meet to finalise the financials and how that works, and how to embed the product via ai to our masjid, its services, volunteering etc. Decided to launch via our website and not wait until app is completed. | Delayed |  | 60% | Need Khalyfa guy to produce scholar endorsement and fine checking for educational content before we proceed any further
SF8
SF9
SF10
SF11
SF12
SF13
SF14
SF15

## OPEX Review Log
Focus Area | Stream | Review Date | Reviewed By | Key Discussion Points / Decisions | Actions Agreed | Next Steps / Deadlines | Person Responsible | Date Closed | OPEX Sign-Off